## Project Timeline
Task | Start Date | End Date | Status | Owner | Notes
Project kickoff | 2026-07-24 | 2026-07-31 | Planned | Project Lead | Finalize scope and team roles
Research and requirements | 2026-07-31 | 2026-08-14 | Planned | Research Lead | Collect requirements and define technical approach
Prototype design | 2026-08-14 | 2026-09-01 | Planned | Architecture Lead | Complete design for AI model, simulator, and backend
Model training baseline | 2026-09-01 | 2026-10-15 | Planned | AI Lead | Train initial baseline model and evaluate performance
Integration sprint | 2026-10-15 | 2026-11-01 | Planned | Backend Lead | Integrate simulator, backend, and data flow
App and hardware demo | 2026-11-01 | 2026-11-30 | Planned | Android/RPi Leads | Prepare end-to-end demo for validation
Testing and documentation | 2026-11-30 | 2026-12-15 | Planned | QA Lead | Validate system and finalize documentation
Final presentation | 2026-12-15 | 2026-12-31 | Planned | Project Team | Prepare thesis and final showcase